## Sheet1
Image Recognition Using OpenCV / (23-10-2017 to 30-11-2017 )

Team	Task’s	Status
Development	-> Requirement gathering	Done	Target 30-10-2017
	-> Understanding Requirement’s	Done
	-> Requirement doc	Review Pending
	-> Detail Design doc	Review Pending
	-> Test Plan doc	Review Pending
	-> Build Iamge using Yocto & Linaro	Pending
	-> Implimenting the Camera Driver	Pending
	-> Interface the Camera.	Pending

Integration	Create GIT server.	Done	Target 30-10-2017
	Create repository using GIT.	Done
	Setup work enivornment using GIT.	Done
	Install sql	Done
	Create Data Base in Sql	Done
	Maintain the Data Base
	Create Gerrit Server
	Create Project in Gerrit
	Add People for Code Review.

Build & Integration		Pending	Target 20-10-2017
	-> Installation of Jenkins and Create the Account	Pending
	-> Generate pub key	Pending
	-> Create New Project	Pending
	-> Source code Management using git repository	Pending
	-> Create batch file to run on Build	Pending
	-> Email configuration	Pending
	-> Install Required plugin	Pending
	->Report the Results.	Pending

Testing	-> Analyzing the requirement document.	Pending	Target 24-10-2017
	-> Test environment setup.	Pending
	-> Writing test cases as per the specifications.	Pending
	-> Analyze the test cases for feasibility of automation	Pending
	-> Writing scripts for automation testing	Pending
	->Writing the Test cases for Camera driver.	Pending
	-> Perform Test execution	Pending
	-> Test Report.	Pending